## Sheet1
| Activity | Hours | Group Member | Category | Is Deliverable
Week 2 | Project Proposal | 10 | All | Misc | yes | ML
| Research, Planning, Discussion | 20 | All | Misc |  | 212 | hours
[6 empty] | 104 | deliverables
iOS
[6 empty] | 0 | hours
[6 empty] | 0 | deliverables
|  | 30 |  |  |  | Misc
Week 3 | Environment Setup | 8 | Chris A | ML |  | 54 | hours
| Environment Setup | 8 | Katrina | ML |  | 10 | deliverables
| Research & Planning | 8 | Chris A | ML
| Research & Planning | 8 | Katrina | ML |  | 266
| Begin writing web scrapers | 4 | Chris A | ML
| Begin writing web scrapers | 4 | Katrina | ML
| Group Meeting | 4 | All | Misc
44
Week 4 | Research & Learning | 6 | Katrina | ML
| Research & Learning | 6 | Chris A | ML
| Twitter web scraper | 8 | Katrina | ML | yes
| Facebook web scraper | 8 | Chris A | ML | yes
| Group Meeting | 4 | All | Misc
32
Week 5 | Research & Learning | 6 | Katrina | ML
| Research & Learning | 6 | Chris A | ML
| Data Clean Up and Normalization | 8 | Chris A | ML | yes
| Data Clean Up and Normalization | 8 | Katrina | ML | yes
| Begin Natural Language Processing | 4 | Chris A | ML
| Begin Natural Language Processing | 4 | Katrina | ML
| Midpoint project review | 4 | Chris A | ML | yes
| Midpoint project review | 4 | Katrina | ML | yes
| Group Meeting | 4 | All | Misc
36
Week 6 | Research & Learning | 6 | Katrina | ML
| Research & Learning | 6 | Chris A | ML
| Natural Language Processing Report | 6 | Katrina | ML | yes
| Natural Language Processing Report | 6 | Chris A | ML | yes
| Begin Testing ML algorithms | 6 | Katrina | ML
| Begin Testing ML algorithms | 6 | Chris A | ML
| Group Meeting | 4 | All | Misc
28
Week 7 | Research & Learning | 6 | Katrina | ML
| Research & Learning | 6 | Chris A | ML
| ML Algorithm Characterization Report | 8 | Katrina | ML | yes
| ML Algorithm Characterization Report | 8 | Chris A | ML | yes
| Group Meeting | 4 | All | Misc
20
Week 8 | iOS integrations | 8 | Katrina | ML | yes
| iOS integrations | 8 | Chris A | ML | yes
| Final Report | 10 | Katrina | ML | yes
| Final Report | 10 | Chris A | ML | yes
| Group Meeting | 4 | All | Misc
40